CTA Roadmap

From Track Record to Registered Commodity Trading Advisor

Prepared: May 2026

This roadmap outlines the chronological steps to transition from an active systematic trader with a public track record to a registered Commodity Trading Advisor managing outside capital. The plan is designed to run in parallel with a full-time career, with most early work requiring no capital outlay.

Phase 1: Foundation Building Now through Month 12 (May 2026 – May 2027)

Track Record & Trading

| Task | Details | Status |
| --- | --- | --- |
| Continue trading strategy | Execute regime signals with discipline. Every month of live, verified performance strengthens your future pitch. Target: 12+ months of continuous IBKR statements. | In Progress |
| Maintain position sizing discipline | No more overleveraging. Consistent contract sizing across all trades. This is what investors scrutinize. | In Progress |
| Document every trade | Ensure the track record page on marketregimes.com captures entry/exit prices, hold periods, and running equity curve. This is your proof. | In Progress |

Website & Online Presence

| Task | Details | Status |
| --- | --- | --- |
| Add contact information | Add a professional email and/or contact form to the website. Investors and potential clients need a way to reach you. | Not Started |
| Update navigation | Remove or rename the "Newsletter" nav link. Keep branding consistent with what the site actually is. | Not Started |
| Add an About / Philosophy page | Tell your story: your background in data science and finance, why you built the regime model, your investment philosophy. People invest in people, not just numbers. | Not Started |
| SEO and discoverability | Write 3-4 evergreen articles on topics like regime-based investing, managed futures basics, or systematic vs. discretionary trading. This helps the site rank and positions you as a thinker, not just a signal. | Not Started |

Personal Development

| Task | Details | Status |
| --- | --- | --- |
| Public speaking / communication | Look into Toastmasters (there are chapters in Bucks County) or a similar program. The goal is not to become a salesman but to be comfortable and clear when explaining your strategy to strangers. | Not Started |
| Start telling people what you do | Practice explaining the strategy in simple language to friends, family, and colleagues. If they understand it in 60 seconds, your pitch is working. | Not Started |
| Network casually | Join online communities for systematic traders, managed futures, and CTAs. Reddit, Twitter/X fintwit, and LinkedIn are all free. Comment, share insights, build name recognition. | Not Started |

Legal & Structural Prep

| Task | Details | Status |
| --- | --- | --- |
| Form an LLC | Register a Pennsylvania LLC for your future CTA business. Cost is approximately $125. This separates personal and business liability. Pick a name and reserve it. | Not Started |
| Open a business bank account | Once the LLC is formed, open a dedicated business bank account. Keeps finances clean from day one. | Not Started |
| Research E&O insurance | Errors and omissions insurance for investment advisors. Get quotes so you know the cost. You may not need it until you have clients, but know the landscape. | Not Started |

Phase 2: Friends & Family Pilot Months 12–18 (May 2027 – November 2027)

With 18+ months of live track record, you can begin managing money for up to 15 people under the NFA exemption without registering as a CTA or passing the Series 3.

IBKR Setup

| Task | Details | Status |
| --- | --- | --- |
| Upgrade to Family Advisor account | Convert your IBKR setup to a Family Advisor master account. This lets you trade across linked client accounts from one interface. | Not Started |
| Configure fee structure | Set up automated fee billing in IBKR: management fee (if any) and performance fee with high water mark. Test the mechanics before onboarding real clients. | Not Started |
| Test with one account | Link one family member’s account and practice executing trades across both accounts. Verify allocation works correctly before scaling. | Not Started |

Client Onboarding

| Task | Details | Status |
| --- | --- | --- |
| Draft advisory agreement | Create a simple but clear agreement covering: strategy description, fee structure, risks, high water mark definition, termination rights. Consider paying a CTA attorney $2–5K for this. | Not Started |
| Onboard 2–5 family/friends | Start small. Help each person open an IBKR account with margin and futures permissions. Walk them through what to expect, including drawdowns. | Not Started |
| Set expectations on volatility | Have an explicit conversation with every client about drawdowns. Show them the -38% period. If they can’t stomach it hypothetically, they are not the right client. | Not Started |

Create Your Pitch

| Task | Details | Status |
| --- | --- | --- |
| Build a one-page strategy overview | A clean, professional PDF: what the strategy does, historical performance, fee structure, and how to get started. This is your leave-behind document. | Not Started |
| Create a 5-minute verbal pitch | Practice explaining your strategy, track record, and value proposition in under 5 minutes. Cover: what you trade, why it works, what the risks are, and what the fees are. | Not Started |
| Prepare for tough questions | Anticipate and practice answering: What’s your worst drawdown? What happens in a crash? Why futures instead of ETFs? What if you die or get sick? Have you ever deviated from the system? | Not Started |
| Record yourself | Film yourself giving the pitch. Watch it. Cringe. Fix it. Repeat until you sound confident and clear, not rehearsed. | Not Started |

Phase 3: CTA Registration Months 18–24 (November 2027 – May 2028)

With 2 years of live performance and a working pilot with family accounts, it is time to formalize the business and remove the 15-client cap.

Series 3 Exam

| Task | Details | Status |
| --- | --- | --- |
| Purchase study materials | Kaplan or a similar Series 3 prep course. Budget $150–300. The exam covers futures market fundamentals, regulations, and trading rules. | Not Started |
| Study and pass Series 3 | 120 questions, 2.5 hours, need 70% on each section. Given your active trading experience, 4–6 weeks of study should be sufficient. | Not Started |

NFA Registration

| Task | Details | Status |
| --- | --- | --- |
| Register with NFA | File Form 7-R, pay $200 registration fee plus ~$750 annual membership dues. Designate a security manager for online access. | Not Started |
| Prepare disclosure document | Required by NFA. Covers your strategy, risks, fees, track record, and background. Hire a CTA compliance attorney to draft or review this. Budget $2–5K. | Not Started |
| Submit disclosure document to NFA | NFA reviews before you can solicit new clients. Allow time for potential revisions. | Not Started |
| Obtain E&O insurance | Now that you are registered, this becomes more important. Protects against client lawsuits. | Not Started |

Business Operations

| Task | Details | Status |
| --- | --- | --- |
| Set up business infrastructure | Professional email, basic CRM or spreadsheet to track client communications, quarterly reporting template for client statements. | Not Started |
| Create client reporting template | Monthly or quarterly report showing account performance, current regime status, trades executed, and comparison to benchmarks. Automate as much as possible. | Not Started |
| Define minimum account size | Recommend $25–50K minimum given futures margin requirements and position sizing needs. Document this in your disclosure. | Not Started |

Phase 4: Growth & Client Acquisition Months 24+ (May 2028 onward)

With full registration, a 2+ year auditable track record, and proven operational experience from the family pilot, you are ready to take on outside clients.

Client Acquisition

| Task | Details | Status |
| --- | --- | --- |
| Let the website work for you | Your track record page is your best salesperson. Continue publishing regime updates. Interested people will reach out through your contact page. | Not Started |
| List on CTA databases | Register on platforms like BarclayHedge, Autumn Gold, IASG, and NilssonHedge where allocators search for CTA managers. Many are free for managers to list. | Not Started |
| Attend CTA Expo or similar events | Now you have the numbers and the license. Events like CTA Expo in New York are a train ride away and designed to connect emerging managers with allocators. | Not Started |
| Explore capital introduction firms | Cap intro services connect managers with investors for a fee or revenue share. Worth exploring once you have $1–2M AUM and want to scale faster. | Not Started |
| LinkedIn content strategy | Share market insights, regime updates, and educational content about systematic trading. This builds credibility with the professional investor audience. | Not Started |

Scaling

| Task | Details | Status |
| --- | --- | --- |
| Target: $5–10M AUM | At 1% management + 20% performance, $10M AUM in a good year generates $300–600K+ in fees. This is the level where the CTA can replace or exceed your salary. | Not Started |
| Consider dropping management fee | A 0% management / 20–25% performance fee structure is a powerful client acquisition tool. You only get paid when they make money. Evaluate once AUM is sufficient. | Not Started |
| Evaluate full-time transition | When fee income consistently approaches or exceeds your salary for 6–12 months, the transition to full-time CTA becomes a real option. Not before. | Not Started |
| Annual disclosure document update | NFA requires annual updates to your disclosure document. Keep performance records current and accurate. | Not Started |

Key Milestones Summary

| Target Date | Milestone | Why It Matters |
| --- | --- | --- |
| Dec 2026 | 12 months live track record | Minimum credible sample for serious conversations |
| May 2027 | 18 months + first family accounts live | Proof of concept with real money under management |
| Nov 2027 | Series 3 passed | Removes the 15-client cap and enables full registration |
| Early 2028 | NFA registration complete | Legally able to solicit and manage outside client money |
| Mid 2028 | First CTA Expo or investor event | Face-to-face with allocators who write real checks |
| 2028–2029 | $5–10M AUM target | Fee income approaches or exceeds current salary |

Estimated Costs

| Item | Low | High |
| --- | --- | --- |
| PA LLC formation | $125 | $125 |
| Series 3 exam fee | $130 | $130 |
| Series 3 study materials | $150 | $300 |
| NFA registration (Form 7-R) | $200 | $200 |
| NFA annual membership dues | $750/yr | $750/yr |
| CTA compliance attorney (disclosure doc) | $2,000 | $5,000 |
| E&O insurance (annual) | $1,000 | $3,000 |
| CTA Expo registration (Manager) | TBD | TBD |
| Total first-year setup | ~$4,400 | ~$9,500 |

Note: All costs are approximate and subject to change. The total first-year setup cost of $4,400–$9,500 is remarkably low for launching a business with six-figure income potential.